## ACTION PLAN
ACTION PLAN FOR IMPLEMENTING THE RECOMMENDATIONS OF THE NATIONAL ML/TF RISK ASSESSMENT
Overall objective: Mitigate money laundering and terrorism financing risks in Serbia
Relevant related planning document / public policy document |  |  |  | MoneyVal Fifth Round Mutual Evaluation Report for Serbia
National Strategy against Money Laundering and the Financing of Terrorism and the related Action Plan
Money laundering risk assessment (ML NRA)
Terrorist Financing risk assessment (TF NRA)
Indicator at the level of the overall objective (indicator of effect): |  |  |  | Base value: |  | Target value:
All recommendations at the level of technical compliance are fulfilled by September 2018, a positive and substantial progress in the implementation of the recommendations at the level of effectiveness of the system demonstrated by December 2020 |  |  |  | Serbia has achieved some progress in addressing deficiencies in the system for fight against money laundering and terrorism financing, but many necessary and important changes are still in a preliminary consultation phase |  | Significant further progress achieved in the fulfillment of the MoneyVal recommendations
|  |  |  | Base year: 2018 |  | Year of fulfillment of the general aim: June 2018 / December 2020
Source of verification: |  |  |  | MoneyVal enhanced follow-up report on Serbia
FATF (ICRG) report
Coordination Team report on implementation of MoneyVal recommendations
Source of threat/vulnerability | Measure No | Measure | Activity No | Activities to implement measures | Lead institution | Partners in the implementation of the activity | Indicator at the level of activity | Source of verification | Resources required | Activity implementation timeline | NOTE: related to activities in other APs
COOPERATION OF RELEVANT AUTHORITIES, NATIONAL RISK ASSESSMENT AND THE ANALYSIS OF THE AML/CFT SYSTEM EFFICIENCY AND EFFECTIVENESS
No body in place to coordinate and ensure efficient cooperation between the competent AML/CFT authorities | 1.1 | Establish a Coordination Body in line with Article 70 of the AML/CFT Law | 1.1.1 | Pass a Government conclusion/decision to establish a Coordination Body | Serbian Government | Ministry of Finance - APML | Government conclusion/decision | Government conclusion/decision | No additional costs - to be covered by current staff within their current jobs | July 2018 | Priority activity
No monitoring of implementation of AML/CFT activities | 2.1 | Coordination Body supervises the implementation of this AP | 2.1.1 | Submission of reports by competent institutions to the Coordination Body about the implementation of activities | all lead institutions |  |  |  | No additional costs - to be covered by current staff within their current jobs | On a quarterly basis | Priority activity
|  |  | 2.1.2 | Coordination Body to analyse reports submitted and prepares a consolidated report to be submitted to the Government | Coordination Body | Serbian Government | AP activity implementation reports | Report of the Coordination Body | No additional costs - to be covered by current staff within their current jobs | On a quarterly basis | Priority activity
Regular updates to the ML/TF NRA in line with Article 70 of the AML/CFT Law | 3.1 | Update the ML/TF NRA | 3.1.1 | Updating of the ML/TF NRA | Serbian Government | Competent state authorities and private sector representatives (chambers, professional associations, etc.) | ML/TF NRA updated | Competent authorities’ work reports | Costs of each individual NRA will be shown therein | December 2020 | Priority activity
No review of the AML/CFT system effectiveness | 4.1 | Do a review of the AML/CFT system effectiveness | 4.1.1 | Develop an annual review of effectiveness and efficiency of the AML/CFT system | APML, MoI, RPPO, Supreme Court of Cassation, MoJ, supevisors | Coordination Body | Report on the review of the AML/CFT system effectiveness | APML website | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from April 2019
RECORD KEEPING AND STATISTICS
No comprehensive and consistent records of all LEAs (joint registers of perpetrators and/or criminal offences with a breakdown of mandatory statistics) | 5.1 | Improve the keeping of records and development of statistical reports | 5.1.1 | Analysis of the keeping of records and development of statistical reports to date | MoJ, MoI, RPPO, Supreme Court of Cassation | Security Information Agency, MoF | Deficiencies found in the manner of record and statistics keeping to date, and recommendations developed for improvements | Analysis developed | No additional costs - to be covered by current staff within their current jobs | October 2018 | Priority activity
|  |  | 5.1.2 | Determination of a required level of comparable data to be kept as statistics in the records of all authorities |  |  | List of comparable data to be kept as statistics in the records of all authorities defined | List developed Individual contributions of involved authorities with a list of data to be exchanged | No additional costs - to be covered by current staff within their current jobs | November 2018 | Priority activity
| 6.1 | Establish a single system of statistical monitoring of ML and TF cases (track record) from the initial information - suspicious activity report (e.g. SAR, citizen information, customs control report) to the court decision | 6.1.1 | Establishment of a working group and definition of a single methodology for the development of reports | MOI, RPPO, Supreme Court of Cassation, APML | MoJ, MoF - Tax Administration, Directorate for Management of Seized/Confiscated Assets, BIA | Interagency working group set up and single methodology for the development of reports defined | WG meeting reports, Methodology document | No additional costs - to be covered by current staff within their current jobs | November 2018 | Priority activity
|  |  | 6.1.2 | Development of uniform forms for reporting about ML and TF cases |  |  | Uniform forms shared with all competent institutions | Uniform forms | No additional costs - to be covered by current staff within their current jobs | November 2018 | Priority activity
|  |  | 6.1.3 | Development of guidelines for preparation for statistical reports (guidelines to fill-out the forms, timelines, how the forms will be submitted etc.) |  |  | Guidelines to prepare statistical reports shared with all competent institutions | Guidelines | No additional costs - to be covered by current staff within their current jobs | November 2018 | Priority activity
|  |  | 6.1.4 | Creation or purchase of a software application for statistical monitoring of ML and TF cases | APML | Supreme Court of Cassation, RPPO, MoI, BIA, VBA, VOA, Tax Administration, Customs Administration, NBS, Securities Commission, AML/CFT supervisors, State Audit Institution, ACAS and Directorate for Management of Seized/Confiscated Assets | Software application in place | Tracking of cases through the software application | Using the available resources/project/international partners | December 2019 | Priority activity
No availability of beneficial ownership information | 7.1 | Establish a centralised records of beneficial owners | 7.1.1 | Adopt a proposal for alaw governing centralised records of BO | Ministry of Economy | Serbian Government, | Proposal for a law governing centralised records of BO adopted | Proposal for a law governing centralised records of BO adopted | No additional costs - to be covered by current staff within their current jobs | July 2018
|  |  | 7.1.2 | Establishment of centralised records of beneficial owners | SBRA, Ministry of Economy |  | Centralised records of beneficial owners established | Reports of competent state authorities | No additional costs - to be covered by current staff within their current jobs | January 2019
|  |  | 7.1.3 | Passage of by-legislation to specify access to centralised records of BO | Ministry of Economy |  | Access to the centralised records ensured in accordance with the by-legislation | By-law | No additional costs - to be covered by current staff within their current jobs | December 2018
IMPROVEMENT OF COORDINATION AND COOPERATION BETWEEN AND EFFECTIVENESS OF STATE AUTHORITIES
Ineffective parallel financial and criminal investigations | 8.1 | Improve the conduct of the pre-investigative proceedings by tracing money flaws and up-to-date keeping of statistics | 8.1.1 | Amendment to the Mandatory Instruction concerning the methodology of collecting, recording, processing and use of crime suppression data | MoI (police directorates, SATIT) | Public Prosecutors’ Offices | Amended mandatory instructions shared with all regional police directorates | Mandatory instructions amended | No additional costs - to be covered by current staff within their current jobs | November 2018
|  |  | 8.1.2 | Introduction of obligation to record data concerning the detected sources of income together with the crime report [referral] (as an annex to the form with information on the known and unknown origin) - using the method of determination of net value of income and expenditure and lifestyle | MoI | APML, Tax Administration | Form of the crime report amended to include a section on the known sources of funds, shared with all competent authorities | MoI annual reports, MoI monthly bulletin with crime figures overview (MoI bulletin of events, phenomena and measures taken) | No additional costs - to be covered by current staff within their current jobs | Continuously
|  |  | 8.1.3 | Passage of a mandatory instruction for the police and General Mandatory Instruction of the RPPO concerning consistent conduct of criminal prosecution against legal entities involved in ML and TF crimes | MoI, Public Prosecutors’ Offices |  | Mandatory Instruction for the police shared with police directorates, the RPPO General Mandatory Instruction shared with competent public prosecutors’ offices | Mandatory Instruction for the police RPPO General Mandatory Instruction | No additional costs - to be covered by current staff within their current jobs | December 2018
| 9.1 | Conduct proactive financial investigations | 9.1.1 | Passage of a mandatory instruction for prosecutors requiring them explicitly to conduct parallel financial investigations in the early stages of the proceedings | MoI | APML, Tax Administration | Mandatory instruction for prosecutors passed | Mandatory Instruction | No additional costs - to be covered by current staff within their current jobs | October 2018
|  |  | 9.1.2 | Passage of a mandatory instruction for police action upon receipt of information that a crime has been committed, and development of instructions concerning operational procedures in conducting financial investigations | RPPO |  | Mandatory instructions passed | Mandatory instruction | No additional costs - to be covered by current staff within their current jobs | October 2018
|  |  | 9.1.3 | Inclusion of financial forensics in the pre-investigative and investigative procedure in order to identify illegal cash placement patterns and to follow money flows | MoI, RPPO |  | Increased number of investigations involving financial forensics Number of reports made by financial forensics | Financial forensics’ reports | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from July 2018
|  |  | 9.1.4 | Inclusion of Financial Investigations Unit’s police officers in the early stage of the pre-investigative proceedings, and making all outcomes of the criminal investigation accessible and usable | MoI |  | Increased number of investigations where Financial Investigations Unit is involved in early stages of the proceedings | Financial Investigations Unit’s reports | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from July 2018
|  |  | 9.1.5 | Annual work programmes and plans should prioritise handling of ML cases | MOI, RPPO, Supreme Court of Cassation |  | Number of ML crime reports received, number of investigations started, number of indictments and court decisions on an annual basis, ML prioritised in AML/CFT authorities’ annual work programmes and plans | Annual work reports | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from October 2018
Insufficient coordination of AML authorities | 10.1 | Create conditions to improve interagency cooperation | 10.1.1 | Signing of new and amendment of current cooperation agreements between relevant state authorities with the aim of involving representatives of authorities in the operation of investigative teams | MoI, RPPO | Supreme Court of Cassation, MoF - Tax Administration, APML, Customs Administration, SBRA, ACAS, NBS, MTTT | Cooperation agreements concluded | Institutions’ annual reports Annual progress reports | No additional costs - to be covered by current staff within their current jobs | December 2018
| 11.1 | Create preconditions to improve cooperation with other AML institutions | 11.1.1 | Signing of cooperation agreements between the APML and Chamber of Authorised Auditors, Chamber of Public Notaries, Serbian Bar Chamber, Ministry of Construction, Infrastructure and Communication | APML | CAA, CPN, SBC, MCIC | Cooperation agreements signed | Cooperation agreements APML annual report | No additional costs - to be covered by current staff within their current jobs | September 2018
| 12.1 | Improve cross-border cash transportation control measures | 12.1.1 | Development of a list of indicators for recognising suspicious transactions related to reported and unreported crossborder transportation of cash and negotiable instruments | Customs Administration Border Police Directorate | APML | Indicators developed and shared with all CA and BPD outposts Increased number suspected ML cases | CA and BPD reports | No additional costs - to be covered by current staff within their current jobs | September 2018 | See 2.31 of the AP for implementing Moneyval recommendations - June 2018
|  |  | 12.1.2 | Conclusion of cooperation agreements between the RPPO, CA, BPD and APML on handling suspicious crossborder transportation of cash and negotiable instruments | Customs Administration, Republic Public Prosecutor’s Office, APML, Border Police Directorate | RPPO, APML, Border Police Directorate | Cooperation agreement concluded, number of CA reports on suspicious cross-border transportation of cash and negotiable instruments increased | Cooperation agreement concluded | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from November 2018
| 13.1 | Improve operational cooperation | 13.1.1 | Establishment of ad hoc task forces | MoI, RPPO, National Geodetic Institute, MoF - TA, APML, MoF - CA, SBRA |  | Number of established task forces Number of representatives of competent authorities involved in the operation of the task forces Number of investigations opened as a result of operation of the task forces | Task force work reports Annual reports of the authorities involved in the operation of the task forces | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from September 2018
|  |  | 13.1.2 | Development of a network of liaison officers in relevant authorities |  |  | A network of liaison officers created, number of liaison officers in relevant authorities | Annual work reports | Liaison officer: to be covered by current resources (salary and benefits) - No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 13.1.3 | Allowing access to necessary databases of relevant authorities through liaison officers - MoI, MoF - TA, SBRA, Justice Information System, National Geodetic Institute - Real Estate Cadastre |  |  | Access to databases allowed to liaison officers | Annual work reports | No additional costs - to be covered by current staff within their current jobs / potential costs to be determined subsequently in line with the overall objective achievement timeline | In line with the overall objective achievement timeline
Lack of cooperation agreements with foreign countries/jurisdictions in relation to AML/CFT (FATF R40) | 14.1 | Agreements to be signed between national AML/CFT supervisors and foreign AML/CFT supervisors | 14.1.1 | Signing of agreements signed between national AML/CFT supervisors and foreign AML/CFT supervisors | AML/CFT supervisors (those who have no agreements) | Foreign supervisors | Efficient cooperation between national and foreign supervisors established | Agreements between national AML/CFT supervisors and foreign AML/CFT supervisors signed | No additional costs - to be covered by current staff within their current jobs | End of 2019 | Priority activity
Insufficient knowledge of AML/CFT authorities of cross-border threats in accordance with NRA | 15.1 | Share with the competent authorities and institutions a breakdown of countries by various threat levels as found by the NRA | 15.1.1 | Sharing of the list of identified countries | APML |  | The list shared with relevant authorities | Implementation report | No additional costs - to be covered by current staff within their current jobs | September 2018
|  |  | 15.1.2 | Establishment of a mechanism for exchanging information in relation to the list of identified countries | APML, BPD, CA | NBS, Supervisory authorities | Number of meetings held Number of information reports exchanged | Meeting reports | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from September 2018
Lack of feedback from judicial authorities concerning the economic offence reports | 16.1 | Improve coordination between the APML, supervisors and judicial authorities | 16.1.1 | Conclusion of agreements between the APML, supervisors, RPPO and Commercial Appellate Court about the handling of economic offence cases stemming from application of the AML/CFT Law and about provision of feedback | APML, supervisors, RPPO, Commercial Appellate Court |  | Cooperation agreement concluded Number of feedback reports shared | Cooperation agreement Annual reports | No additional costs - to be covered by current staff within their current jobs | November 2018
|  |  | 16.1.2 | Development of uniform forms concerning the handling of economic offence cases stemming from application of the AML/CFT Law | APML, relevant supervisors, RPPO, Commercial Appellate Court |  | Uniform forms shared with all competent institutions | Uniform forms | No additional costs - to be covered by current staff within their current jobs | December 2018
Sanctioning policy | 17.1 | Ensure consistency of case law (court practice) | 17.1.1 | Regular publication of bulletins and professional publications concerning ML cases and convictions | Supreme Court of Cassation | International partners | Number of published bulletins and professional publications | Bulletins and publications | No additional costs - to be covered by current staff within their current jobs | Continuously
|  |  | 17.1.2 | Holding of consultations on particularly important court decisions that can be taken as precedents |  |  | Number of consultations | Reports on the consultations held | No additional costs - to be covered by current staff within their current jobs / support by international partners | Continuously
Lack of money laundering typologies in accordance with the NRA | 18.1 | Develop sectoral ML typologies and case studies in accordance with the new NRA | 18.1.1 | Development of ML typologies and case studies | APML, MoI, Public Prosecutors’ Offices |  | ML typologies and case studies developed | ML typologies document | No additional costs - to be covered by current staff within their current jobs | December 2018
STRENGTHENING OF ADMINISTRATIVE, MATERIAL AND TECHNICAL CAPACITITES AND IMPROVOMENT OF OPERATION OF SUPERVISORS
Insufficient number of APML staff | 19.1 | Increase APML administrative capacities | 19.1.1 | Recruitment of new staff in accordance with the current job classification (currently 29 posts involving 37 staff members; 6 more financial intelligence analysts, strategic analysts and inspectors should be recruited) | Ministry of Finance | Serbian Government | Number of APML staff increased | APML Information Bulletin | APML BudgetRSD 17.700.00 annually, as of March 2019 | March 2019
No special organisational unit in place in the APML engaged in strategic analysis | 20.1 | Establish a special APML organisational unit to deal with strategic analyses | 20.1.1 | Modification of the APML organisational structure | APML |  | APML organisational structure modified | APML Information Bulletin | To be determined | June 2019
|  |  | 20.1.2 | Delivery of strategic analysis training | APML | International partners | Number of trainings delivered | Training reports Training evaluation forms | Costs of implementation of this activity will be covered by international partners and donors | Continuously
|  |  | 20.1.3 | Regular development and publication of APML strategic analyses | APML |  | Strategic analyses developed and published | APML website | No additional costs - to be covered by current staff within their current jobs | Continuously
Inadequacy of APML databases for the purpose of strategic analyses | 21.1 | Improve the current and purchase new databases | 21.1.1 | Asses the need for necessary databases and resources needed to purchase them | APML | Ministry of Finance | Improved quality of strategic analyses | New databases | No additional costs RSD 30.000.000 earmarked in the 2018 Budget Law | Continuously
|  |  |  | Delivery of training for APML staff for the use of the databases | APML | Ministry of Finance | Number of training for the use of new databases delivered | Training reports Training evaluation forms | See the preceding activity | End of 2019
Inadequate APML capacities in terms of business premises and IT | 22.1 | Relocate the APML to adequate business premises and equip a situation room for training and meetings | 22.1.1 | Refurbishing of the new premises and relocation of the APML and adequate technical equipping of the room | APML | MoF and Government Common Services Administration | Relocation of new premises and delivery of training and meetings | APML | Reallocation of current resources | September 2018
Lack of capacities for assessment of value of seized/confiscated assets | 23.1 | Strengthen the administrative capacities of the Directorate for Management of Seized/Confiscated Assets | 23.1.1 | Engagement of an appraiser for the value of the seized/confiscated assets in line with the Directorate’s jobs classification act | Directorate for Management of Seized/Confiscated Assets | Serbian Government, Ministry of Finance | Appraiser recruited | Employment contract | Budget of the Directorate for Management of Seized/Confiscated Assets - RSD 960.000 per year, as of 2021 - gross salary NOTE: Assessment made based on the value of an average salary in Serbia | December 2020
Failure to conduct risk-based offsite and onsite supervision of obliged entities - casinos and games of chance operators using e-communications | 24.1 | Establish a specialised administrative body to perform the public administration tasks in the games of chance area that will conduct supervision in the AML/CFT area | 24.1.1 | Establishment of a specialised administrative body to perform the public administration tasks in the games of chance area | Ministry of Finance | Serbian Government | A specialised administrative body to perform the public administration tasks in the games of chance area established | Official Gazette of the Republic of Serbia | Job classification: reallocation of the current staff in view of the current employment ban | December 2019
|  |  | 24.1.2 | AML/CFT supervision | Specialised administrative body for games of chance |  | Number of inspections conducted | Work report | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from December 2018
Insufficient level of training for ML/TF risk-based onsite and offsite inspections over obliged entities operating games of chance | 25.1 | Strengthen the administrative capacities for sustainable onsite/offsite inspections over the obliged entities operating games of chance | 25.1.1 | Delivery of training of the staff of the specialised authority (measure 15.1) to conduct inspections related to compliance with the AML/CFT Law with respect to games of chance area | Tax Administration | International partners | Number of trainings delivered | Training reports Training evaluation forms | Costs of implementation of this activity will be covered by international partners | Continuously, starting from September 2018
Inadequate legal provisions on AML/CFT supervision of accountants | 26.1 | Analyse the legal provisions on AML/CFT supervision of accountants | 26.1.1 | Develop a comparative analysis of legal provisions governing AML/CFT supervision of accountants showing the provisions of other countries (good practice examples) | APML |  | Analysis developed | APML annual report | No additional costs - to be covered by current staff within their current jobs | June 2019
Lack of APML human resources to carry out supervision of accountants, auditors and factoring firms | 27.1 | Strengthen APML human resources to carry out supervision of accountants, auditors and factoring firms | 27.1.1 | Recruitment of relevant staff according to the job classification document to carry out the AML/CFT tasks | Ministry of Finance and APML | Serbian Government | APML vacancies filled | Employment contracts APML annual report | Provided for in the budget under activity 19.1.1 | Continuously starting from July 2018 to December 2019
|  |  | 27.1.2 | Delivery of training to the APML supervision department staff so that they acquire the required skills and most recent knowledge to carry out supervision of compliance with the AML/CFT Law |  |  | Number of trainings delivered | Training reports Training evaluation forms | International partners/Republic of Serbia budget - no costs | Continuously starting from July 2018, until December 2019
Lack of staff to carry out supervisory inspection over real estate trade and lease intermediaries | 28.1 | Strengthen administrative capacities in the area of supervisory inspection over real estate trade and lease intermediaries | 28.1.1 | Reallocation of the current inspectors | MTTT | Government, MTTT Secretariat | Reallocation completed | Annual reports | No additional costs - to be covered by current staff within their current jobs | Continuously until December 2020
|  |  | 28.1.2 | Conduct a needs analysis for the required number of AML/CFT staff |  |  | Needs analysis done | Annual reports | No additional costs - to be covered by current staff within their current jobs | Continuously until December 2020
Lack of staff to supervise trade in precious metal items | 29.1 | Strengthen the administrative capacities of the expert and supervisory inspection in the area of precious metal trade | 29.1.1 | Reallocation of the current inspectors | MTTT | Government, Ministry of Economy - Directorate and MTTT | Staff reallocated | Work report of the Directorate Work report of the Market Inspectorate; | No additional costs - to be covered by current staff within their current jobs | May - June 2019
|  |  | 29.1.2 | Conduct a needs analysis for the required number of AML/CFT staff |  |  | Needs analysis done | Work report of the Directorate Work report of the Market Inspectorate; | No additional costs - to be covered by current staff within their current jobs | May - June 2019
Lack of staff to supervise trade in cars | 30.1 | Strengthen administrative capacities in the area of supervisory inspection over trade in cars | 30.1.1 | Reallocation of the current inspectors | MTTT | Government and MTTT | Staff reallocated | Work report of the Market Inspectorate | No additional costs - to be covered by current staff within their current jobs | May - June 2019
|  |  | 30.1.2 | Conduct a needs analysis for the required number of AML/CFT staff |  |  | Needs analysis done | Work report of the Market Inspectorate | No additional costs - to be covered by current staff within their current jobs | May - June 2019
Lack of APML human resources to carry out supervision of factoring firms | 31.1 | Strengthen administrative capacities in the area of supervisory inspection over factoring firms | 31.1.1 | Filling of vacancies in in line with the current jobs classification | APML | Serbian Government | Number of APML staff increased according to the current jobs classification | APML Information Bulletin | See activity 19.1.1. | October 2018
|  |  | 31.1.2 | Delivery of training to new staff of the APML supervision department so that they acquire the required skills and most recent knowledge for carrying out inspections | APML | Serbian Government | Number of trainings delivered | Training reports Training evaluation forms | as part of regular activities | Continuously, until the end of 2019
Transfer of supervisory powers over factoring firms from the APML | 32.1 | Conduct continuous offsite and onsite supervision of factoring firms | 32.1.1 | Performance of offsite inspections by sending out questionnaires | APML | APML | No of offsite inspections | Lead institution’s work reports | Within the current APML budget | Continuously, starting from September 2018
Lack of APML human resources to carry out supervision over accountants and significant staff turnover | 33.1 | Strengthen APML administrative capacities | 33.1.1 | Filling of vacancies in in line with the current jobs classification | APML | Serbian Government | Number of APML staff increased according to the current jobs classification | APML Information Bulletin | See activity 19.1.1. | October 2018
|  |  | 33.1.2 | Delivery of training to new staff so that they acquire the required skills and most recent knowledge | APML | Serbian Government | Number of trainings delivered | Training reports Training evaluation forms | as part of regular activities | Continuously, until the end of 2019
Insufficient number of onsite inspections of accountants | 34.1 | Conduct offsite and onsite supervision of accountants on a continuous basis | 34.1.1 | Intensification of offsite inspections of accountants by distributing the questionnaire | APML | APML | No of offsite inspections | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | Continuously
|  |  | 34.1.2 | Carrying out of AML/CFT onsite inspections of accountants based on a risk matrix |  |  | No of offsite inspections | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | Continuously
Inconsistency between the number of SARs and their quality in obliged entities | 35.1 | Improve the efficiency of monitoring and reporting of suspicious transaction by obliged entities - improvement of SAR quality and quantity in line with identified threats and vulnerabilities | 35.1.1 | Identification of problems when recognising, monitoring and reporting of suspicious transactions | APML |  | Problems encountered by obliged entities when identifying and reporting suspicious transactions identified | APML annual report | No additional costs - to be covered by current staff within their current jobs | Continuously Starting from July 2018, until December 2019
|  |  | 35.1.2 | Specialised training of obliged entities that take into account the identified threats and vulnerabilities | APML | Serbian Chamber of Commerce, MTTT, Association of Serbian Banks, Serbian Bar Chamber, Chamber of Public Notaries, Association of Serbian Insurers, Association of Leasing Companies, NBS | Number of trainings delivered | Training reports Training evaluation forms | Council of Europe project / national and international partners
|  |  | 35.1.3 | Improvement of monitoring of reporting systems and practices used | Supervisory authorities |  | Improvement of the system for identification and reporting of suspicious transactions through an increased number and quality of reported transactions | Supervisors’ annual reports | No additional costs - to be covered by current staff within their current jobs
Lack of necessary resources for further improvement of the Securities Commission’s supervisory function in terms of increasing the number of inspectors, additional training, and improvement of IT, in case of an increase in the number of obliged entities and sectoral risk | 36.1 | Make necessary resources available for the purpose of sustainability and strengthening of the Securities Commission’s supervisory function | 36.1.1 | Strengthening of Securities Commission’s supervisory function | Ministry of Finance/Securities Commission |  | Situation analysis report | Securities Commission annual report | No additional costs - to be covered by current staff within their current jobs | December 2020
|  |  | 36.1.2 | Delivery of training in order to acquire the required skills and knowledge | Ministry of Finance and Securities Commission | International partners | Number of trainings delivered | Training reports Training evaluation forms | No additional costs - to be covered by current staff within their current jobs / support by international partners | Continuously
Insufficient number of inspection of currency exchange offices in accordance with the identified threats and vulnerabilities | 37.1 | Increase the number of offsite and onsite inspections of currency exchange offices | 37.1.1 | Increase in the number of offsite inspections | Tax Administration, and National Bank of Serbia as of 01.01.2019 |  | No of offsite inspections | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | August 2018 and as required
|  |  | 37.1.2 | Increase in the number of onsite inspections |  |  | No of onsite inspections | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | Continuously
Inadequate understanding of AML/CFT legislation by currency exchange offices | 38.1 | Raise awareness of currency exchange offices about their obligations under AML/CFT Law | 38.1.1 | Improve the level of awareness of currency exchange offices and the system of offsite inspections | Tax Administration, and National Bank of Serbia as of 01.01.2019 |  | Reduced number of violations of the law given the better understanding of legislation and obligations under AML/CFT Law. | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | Continuously
Failure to comply with statutory requirements concerning the sanctioning of crimes against economy when starting real estate business | 39.1 | Harmonise by-legislation and other acts with the Law Amending the Law on Real Estate Trade and Lease | 39.1.1 | Adopt the proposed Law | Ministry of Trade, Tourism and Telecommunications | Serbian Government | The proposal for a Law Amending the Law on Real Estate Trade and Lease adopted | The proposal for a Law Amending the Law on Real Estate Trade and Lease adopted | No additional costs - to be covered by current staff within their current jobs | July 2018
|  |  | 39.1.2 | Harmonisation of by-legislation (Rulebook on the Register of intermediaries in the trade and lease of real estate) with the amended Law. |  |  | By-legislation passed | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | July 2018
|  |  | 39.1.3 | Updating of the Register of Intermediaries |  |  | Register of Intermediaries updated | MTTT website | No additional costs - to be covered by current staff within their current jobs | September and October 2018
Insufficient application of AML/CFT legislation by intermediaries | 40.1 | Conduct inspection of intermediaries intensively | 40.1.1 | Development of a risk assessment for intermediaries | Ministry of Trade, Tourism and Telecommunications - Market Inspectorate |  | Risk assessment developed | Market Inspectorate report | No additional costs - to be covered by current staff within their current jobs | August and September 2018
|  |  | 40.1.2 | Supervision plan development |  |  | Supervision plan developed | Market Inspectorate annual work report | No additional costs - to be covered by current staff within their current jobs | September 2018
|  |  | 40.1.3 | Implementation of the supervision plan (verification of risk understanding, performing internal procedures and controls of cash payments) |  |  | Supervision plan implemented | Market Inspectorate report | No additional costs - to be covered by current staff within their current jobs | October and November 2018
|  |  | 40.1.4 | Ordering of measures to remedy the irregularities found |  |  | Measure implemented | Market Inspectorate report | No additional costs - to be covered by current staff within their current jobs | October and November 2018
|  |  | 40.1.5 | Follow-up supervision |  |  | Follow-up supervision performed | Market Inspectorate report | No additional costs - to be covered by current staff within their current jobs | December 2018
Lack of legal basis for transaction reporting to the supervisor by games of chance providers, using e-commmunication and incompliance with FATF R28 (fit and proper) in the games of chance area | 41.1 | Amend the Law on Games of Chance | 41.1.1 | Adoption of a proposal for aLaw Amending the Law on Games of Chance in order to provide for a basis for reporting to the supervisor about transactions by providers using e-communications, and to comply with FATF R28 (fit and proper) in the games of chance area | Ministry of Finance | Serbian Government | Proposal for a Law Amending the Games of Chance Law adopted | Proposal for a Law Amending the Games of Chance Law adopted | No additional costs - to be covered by current staff within their current jobs | July 2019
|  |  | 41.1.2 | Passage of by-legislation in line with the amended Games of Chance Law | Ministry of Finance | Serbian Government | By-legislation passed | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | July 2019
Lack of legal basis for individual investors to be registered as tax payers and to be required to open specific-purpose accounts | 42.1 | Amend the VAT Law and Law on Personal Income Tax. | 42.1.1 | Pass a Law amending the VAT Law in order to introduce individual investors into the register of business entities as taxpayers performing a business with a mandatory registration in the VAT system. | Ministry of Finance | Serbian Government | Amendments to the VAT Law passed | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | 2020
|  |  | 42.1.2 | Adoption of a proposal for a Law Amending the VAT Law and Law on Personal Income Tax in order to prevent conduct of business without opening a specific-purpose account | Ministry of Finance | Serbian Government | Proposal for a Law Amending the VAT Law and Personal Income Tax Law passed | Proposal for a Law Amending the VAT Law and Personal Income Tax Law passed | No additional costs - to be covered by current staff within their current jobs | 2020
Lack of case studies for ML through construction of real estate by individual investors | 43.1 | Conduct case studies and pass indicators for recognising suspicious transactions in the area of construction by individual investors | 43.1.1 | Develop case studies related to ML through investment in the construction in real estate by individual investors. | APML | RPPO | Case study report | APML annual work reports | No additional costs - to be covered by current staff within their current jobs | June 2019 | Priority activity
|  |  | 43.1.2 | Pass suspicious transaction indicators based on the case studies |  |  | Indicators passed | APML website | No additional costs - to be covered by current staff within their current jobs | June 2019 | Priority activity
|  |  | 43.1.3 | Training of obliged entities and supervisors in line with relevant remits of responsibility |  |  | Number of trainings delivered | APML annual work reports | No additional costs - to be covered by current staff within their current jobs | June 2019 | Priority activity
Lack of capacities of lawyers for the collection of data, analysis and reporting in line with the AML/CFT Law | 44.1 | Strengthen the capacities of lawyers to better understand their obligations under the AML/CFT Law | 44.1.1 | Preparation of a questionnaire for lawyers - members of the Serbian Bar Association | Serbian Bar Association (SBA) |  | Questionnaires developed (as a precondition for offsite inspection) | SBA Report | No additional costs - to be covered by current staff within their current jobs | September 2018
|  |  | 44.1.2 | Problem identification in the system of analysis of data and reporting in the AML system | Serbian Bar Association (SBA) |  | Problems in the system of analysis of data and reporting in the AML system identified | SBA Report | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 44.1.3 | Oversight of the system and practices of authorities responsible for reporting in the AML area | Serbian Bar Association (SBA) |  | Regular oversight of the system for compliance of regulations | SBA Report | No additional costs - to be covered by current staff within their current jobs | Continuously
Insufficient oversight of compliance by lawyers with the AML/CFT Law | 45.1 | Conduct offsite and onsite inspection of lawyers | 45.1.1 | Offsite and onsite inspection of lawyers - members of the Serbian Bar Chamber | Serbian Bar Association (SBA) |  | Data obtained in offsite inspections (as a precondition for onsite inspection) | SBA Report | No additional costs - to be covered by current staff within their current jobs | December 2018
Lack of an Action Plan to carry out onsite inspection over public notaries | 46.1 | Carry out onsite AML/CFT supervision, first of all over the elements related to the check of the internal organisation and availability of written risk assessment procedures in every public notary office. | 46.1.1 | Passage of an action plan to envisage measures to be taken by the Chamber with specifically determined objectives and tasks, as well as timelines on a short-term, mid-term and long-term basis. | Chamber of Notaries Public |  | Action plan passed | Action plan passed | No additional costs - to be covered by current staff within their current jobs | July 2018
Lack of legal regulations governing precious stones | 47.1 | Fine tune the regulations governing precious stones and the Law on Precious Metals | 47.1.1 | Establish a working group to analyse the situation | Coordination Body | Government of the Republic of Serbia | Analysis report and recommendation of measures | Report of the president of the Coordination Body | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 47.1.2 | Development of legislative acts in line with working group recommendations |  |  | Proposal for legislative acts |  | No additional costs - to be covered by current staff within their current jobs | March 2019
Imprecise provisions concerning the remit of responsibilities related to to the control of production, trade, purchase and keeping of records on precious metal items, which leads to overlaps in remits of various authorities. | 48.1 | Adopt a proposal for a Law Amending the Law on Precious Metal Item Control | 48.1.1 | Adoption of a proposal for a Law Amending the Law on Precious Metal Items Control | Ministry of Economy - Directorate of Measures and Precious Metals | MTTT, Government of the Republic of Serbia | A proposal for a Law Amending the Law on Precious Metal Items Control adopted | A proposal for a Law Amending the Law on Precious Metal Items Control adopted | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 48.1.2 | Development of by-laws |  |  | By-legislation passed | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | December 2018
Inadequate inspections of business entities trading in precious metal items | 49.1 | Carry out intensive professional supervision and supervisory inspections of business entities trading in precious metal items | 49.1.1 | Passage of a Supervisory Inspection Plan and prioritisation of business entities for inspection based on input data | Directorate of Measures and Precious Metals, Tax Inspection, Customs Administration and Market Inspectorate |  | Analysis of statistics of previous inspections generated by the MTTT IT system (MIMIS), Register of the Directorate of Measures and Precious Metals, comparison with the databases of the SBRA, Tax Administration and Customs Administration. | Work report of MTT, Directorate of Measures and Precious Metals, Tax Inspection, Customs Administration | No additional costs - to be covered by current staff within their current jobs | Starting from July 2018, until February 2019
|  |  | 49.1.2 | Carrying out of professional supervision, onsite supervisory inspections, by checking cash payments and record keeping practices |  |  | Number of inspections in cooperation with the MTTT, Tax Inspection, and Directorate of Measures and Precious Metals | Work report of Directorate of Measures and Precious Metals, Tax Administration, Customs Administration and MTTT | No additional costs - to be covered by current staff within their current jobs | October - November 2018, March, April and December 2019
|  |  | 49.1.3 | Check of cross-border trade in precious metal items and verification of risk understanding |  |  | Number of joint inspection by the MTTT and Customs Administration | Report of the MTTT - Sector for foreign trade, and Customs Administration | No additional costs - to be covered by current staff within their current jobs | November and December 2018, June and July 2019
|  |  | 49.1.4 | Imposition of measures with regard to any irregularities found |  |  | Measures imposed with regard to any irregularities found | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | November and December 2018, February, June and July 2019
|  |  | 49.1.5 | Follow-up supervision |  |  | No of inspections carried out | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | December 2018 and March 2019
Inadequate supervision in the area of car trade | 50.1 | Carry out intensive supervisory inspections of business entities trading in cars | 50.1.1 | Passage of a Supervisory Inspection Plan and prioritisation of business entities for inspection based on input data | Ministry of Trade, Tourism and Telecommunications - Market Inspectorate |  | Analysis of statistics of previous inspections generated by the MTTT IT system (MIMIS), comparison with the databases of the SBRA, Tax Administration and Customs Administration. | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | August and September 2018, march, April, October and November 2019
|  |  | 50.1.2 | Carrying out of onsite supervisory inspections, by checking cash payments and record keeping practices |  |  | Number of inspections carried out in cooperation with the MoI and Road Inspection | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | September and October 2018, February, March, September and October 2019
|  |  | 50.1.3 | Imposition of measures to remedy the irregularities found |  |  | Measures imposed with regard to any irregularities found | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | September and October 2018, February, March, September and October 2019
|  |  | 50.1.4 | Carrying out of follow-up inspections to check compliance with measures imposed |  |  | No of inspections carried out | Report concerning onsite supervision generated from the MTTT IT system (MIMIS) | No additional costs - to be covered by current staff within their current jobs | October 2018, April and December 2019
Complexity of ML/TF methods used by investors in the area of residential and non-residential building construction | 51.1 | Improve the operation of authorities to better recognise ML/TF by learning from ML/TF typologies specific for investors in the area of residential and non-residential building construction | 51.1.1 | Development and publication of the typologies document | APML, RPPO, MoI, Tax Administration | Ministry of Construction | ML typologies and case studies developed | APML annual work reports | No additional costs - to be covered by current staff within their current jobs | December 2018
Inadequate supervision of business entities manufacturing and trading in precious metal items | 52.1 | Carry out supervision and training of business entities trading in precious metal items in accordance with the risk assessed through onsite inspections | 52.1.1 | Development of an AML/CFT Training Plan to be used by APML, MTTT and the Directorate together with the Serbian Goldsmith Association (including the number of participants, venue, preparation and organisation of training delivery) | MTTT | Ministry of Economy - Directorate of Measures and Precious Metals, Serbian Goldsmith Association and APML | Coordinated activity by all authorities | Serbian Chamber of Commerce website | No additional costs - to be covered by current staff within their current jobs | September 2018 and February 2019
|  |  | 52.1.2 | Identification of potential training material and sources |  |  | Preparation of presentations and printing out of materials (Serbian Goldsmith Association) | Work report of the Market Inspectorate | No additional costs - to be covered by current staff within their current jobs - Printing costs - Serbian Goldsmith Association | September 2018 and February 2019
|  |  | 52.1.3 | Training delivery |  |  | Number of trainings delivered | Training reports Training evaluation forms | APML Budget - RSD 150,000 annually, for organising 4 training events/workshops | October and November 2018, March, October and November 2019
|  |  | 52.1.4 | Carrying out of inspections |  |  | No of inspections | Work report of the Market Inspectorate | No additional costs - to be covered by current staff within their current jobs | Continuously
Inadequate supervision of business entities trading in cars | 53.1 | Carry out supervision and training of business entities trading in cars in accordance with the risk assessed through onsite inspections | 53.1.1 | Development of an AML/CFT Training Plan to be used by APML, MTTT and Serbian Chamber of Commerce (including the number of participants, venue, preparation and organisation of training delivery) | MTTT | APML and Serbian Chamber of Commerce | Coordinated activity by all authorities | Serbian Chamber of Commerce website | No additional costs - to be covered by current staff within their current jobs | September 2018, January and November 2019
|  |  | 53.1.2 | Preparation and distribution of awareness raising material |  |  | Preparation of presentations and printing out of materials (Serbian Chamber of Commerce) | Work report of the Market Inspectorate | APML Budget - RSD 100,000 for 2018, and 300,000 for 2019, costs of printing | September 2018, January and November 2019
|  |  | 53.1.3 | Training delivery |  |  | Presentations, workshops, discussions (APML, MTTT, Serbian Chamber of Commerce) | Work report of the Market Inspectorate | see activity 52.13 | October 2018, February and December 2019
|  |  | 53.1.4 | Carrying out of inspections |  |  | No of inspections | Work report of the Market Inspectorate | No additional costs - to be covered by current staff within their current jobs | Continuously
Insufficiently efficient BO identification in complex ownership structures | 54.1 | Improve identification of BOs | 54.1.1 | Pass common guidelines for identifying BOs | APML | Supervisory authorities | Pass common guidelines | APML website | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 54.1.2 | Hold adequate training for obliged entities |  |  | Number of trainings delivered | Training reports and Training evaluation forms | No additional costs - to be covered by current staff within their current jobs / support by a Council of Europe project | June - June 2019
Insufficient awareness of new products in the financial system (unit-linked products) | 55.1 | Follow the introduction of new products in the financial system | 55.1.1 | Carrying out of a special analysis of life insurance companies that have introduced unit-linked products | National Bank of Serbia | Serbian Insurers’ Association | Internal (NBS) ML/TF risk assessment for the unit-linked products introduced to date | Questionnaire, regular reporting, operation checks | No additional costs - to be covered by current staff within their current jobs | By the end of 2018
|  |  | 55.1.2 | Carrying out of regular supervision based on the data obtained from the questionnaire |  |  | Level at which the unit-linked product analysis was included in the ML/TF risk assessment of insurance companies | Questionnaire, info summaries, internal notes, operation checks | No additional costs - to be covered by current staff within their current jobs | Continuously
Inconsistency of certain acts passed by supervisors with the new NRA | 56.1 | Make supervisor acts compliant with the NRA, where necessary | 56.1.1 | The process of making the acts (guidelines, indicators, supervision plans, risk matrices, STR forms etc.) compliant with the NRA, as necessary | Supervisory authorities (APML, Tax Administration, DNFBP supervisors) |  | Acts passed by each specific supervisor | Acts published | No additional costs - to be covered by current staff within their current jobs | December 2018
Lack of statistics in electronic form | 57.1 | Introduce statistics in electronic form | 57.1.1 | Implementation of an electronic IT system for electronic processing of statistics to be delivered by public notaries to teh Serbian Chamber of Public Notaries, in line with the Public Notary Book of Rules | Chamber of Notaries Public | MoJ | Electronic IT system established | Report of the Chamber of Public Notaries | Republic of Serbia budget - no costs | May 2019 | Priority activity
Lack of a centralised and efficient database needed to implement the AML/CFT Law and Law on Freezing of Assets with the Aim of Preventing Terrorism and Proliferation of WMD | 58.1 | Introduce a centralised and efficient database needed to implement the AML/CFT Law and Law on Freezing of Assets with the Aim of Preventing Terrorism and Proliferation of WMD | 58.1.1 | Centralisation, networking and allowing access to the application for search of the following databases: lists of designated persons, countries against which the United Nations, Council of Europe or other international organisations have applied sanctions, embargo or similar measures; countries designated by credible institutions (FATF, Council of Europe, etc.) as not applying adequate AML/CFT measures; countries designated by credible institutions (FATF, Council of Europe, etc.) as supporting or financing terrorist activities or organisations and countries designated by credible institutions (e.g. World Bank, IMF) as countries with a high level of corruption and crime. | APML |  | Application developed and access enabled on the APML website | APML website | Costs of implementation of this activity will be covered by international partners | December 2020
TRAINING
Insufficient awareness of the public, private and NPO sector in the existence of ML/TF risks | 59.1 | Raise awareness of the public, private and NPO sectors about ML/TF threats | 59.1.1 | Development of awareness raising materials - flyers and brochures | APML | MoF, MoJ, MoI, Ministry of Economy, Serbian Chamber of Commerce, foreign partners | Number of materials printed out and disseminated | Printed material Report on the dissemination of materials | APML Budget - RSD 300,000 annually, for printing and distribution (account 423) | December 2018
|  |  | 59.1.2 | Awareness raising and training of the public, private and NPO sectors through workshops |  |  | 4 workshops delivered | Workshop reports Training evaluation forms | APML Budget - RSD 150,000 annually, for 4 workshops a year | Continuously, starting from the III quarter of 2018 | In line with activities 4.1.1.3, 4.1.1.5 and 4.1.5 in the Action Plan for implementing the National AML/CFT Strategy
|  |  | 59.1.3 | Delivery of training for APML |  |  | 2 advanced training events carried out | Training reports Training evaluation forms | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from the III quarter of 2018
|  |  | 59.1.4 | Strengthening of communication and cooperation between the public and civil sectors in potential abuse for TF, by organising round tables, consultations and other activities with civil society organisations | Office for Cooperation with Civil Society | APML | Number of round tables, meetings, consultations and other activities organised | Reports by lead authorities | Link: Activity 1.3.2 in the AML/CFT Strategy AP No additional costs | Continuously | Part of the trainings will be implemented in line with activities under 1.3.2 in the National AML/CFT Strategy Action Plan
Insufficient level of AML/CFT training | 60.1 | Strengthen the capacities of relevant authorities and continuous professional training of the AML/CFT staff | 60.1.1 | Provision technical capacities and know-how to the APML | APML |  | Technical capacities and know-how provided | Reports by lead authorities | Link: Activity 3.3.1.2 in the AML/CFT Strategy AP Partly from the IPA 2015 (FIU Core Project)/the rest: from current resources | Continuously, in line with the overall objective achievement timeline | Budget as defined by the Action Plan for the Implementation of the National Strategy against Money Laundering and Terrorism Financing, activities under 3.3.1.2 and IPA 2015
|  |  | 60.1.2 | Delivery of advance training for the Prosecutor’s Office for Organised Crime, BIA, MoI Service Against Terrorism and Extremism, VBA and APML with the aim of adjusting to the new CFT concepts (e.g. use of crypto currencies for TF purposes) | POOC, BiA, MoI SATE, VBA and APML |  | Number of trainings delivered | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, in line with the overall objective achievement timeline | Part of the trainings will be implemented in line with activities under 2.3.4 and 3.2.1 in the National AML/CFT Strategy Action Plan
| 61.1 | Improve the capacities for proactive financial investigations against individuals and entities and assess the use of circumstantial evidence in the trial stage | 61.1.1 | Delivery of training on financial investigations, use of financial intelligence, presentation of evidence in criminal proceedings for ML, analysis of financial flows and criminal organisation financial flow modelling, stand-alone ML investigations | Police Academy; Supreme Court of Cassation, RPPO, MoI | International partners | Two cycles of advanced training delivered to deputy public prosecutors in anti-corruption departments and POC and special MoI departments involved in financial investigations and money laundering | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018
|  |  | 61.1.2 | Delivery of training about the importance of circumstantial evidence - analysis and inferences based on circumstantial evidence; passing of a decision on the acceptability of evidence at the preparatory hearing; assessment of forensic evidence, net value analysis |  |  | Two cycles of advanced training for deputy public prosecutors and judges at the POC and Belgrade Higher Court Special Department | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018
|  |  | 61.1.3 | Delivery of training for assessment and security of the value of proceeds from crime until the final court decision |  |  | 1 cycle of training for staff of the MoI special departments involved in financial investigations and money laundering and public prosecutors | Training report Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018
|  |  | 61.1.4 | Delivery of training for prosecuting legal entities |  |  | Two cycles of training delivered to public prosecutors and MoI staff involved in investigating economic and financial crime including money laundering | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018
| 62.1 | Improve the capacities of public prosecutors’ offices to collect data from electronic (digital) sources and capacities of courts in terms of deliberating on and making decisions based on such evidence | 62.1.1 | Delivery of training to public prosecutors about the collection of data from electronic/digital sources, including coded and encrypted data located outside Serbia | Police Academy, High Judicial Council, State Prosecutorial Council | Supreme Court of Cassation, RPPO, international partners | 1 cycle of basic training and one cycle of advanced training for deputy public prosecutors delivered | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018, ending in December 2019
|  |  | 62.1.2 | Delivery of training to judges on deliberating and decision-making based on the data obtained from from electronic/digital sources, including coded and encrypted data located outside Serbia |  |  | 1 cycle of basic training and one cycle of advanced training for judges delivered | Workshop reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018, ending in December 2019
|  |  | 62.1.3 | Delivery of training for prosecuting ML through crypto-currencies, e-money and virtual currencies intended for public prosecutors and judges |  |  | 1 cycle of basic training and one cycle of advanced training for deputy public prosecutors and judges delivered | Workshop reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018, ending in December 2019
| 63.1 | Improve the capacities of authorities involved in financial investigations concerning the assets of suspects located abroad, provision of MLA, including seizure/confiscation | 63.1.1 | Development of guidance for public prosecutors for the provision of MLA | RPPO | International partners | Guidelines developed according to the standards and institutes of MLA provided for under relevant conventions | Guidance for public prosecutors for the provision of MLA | No additional costs - to be covered by current staff within their current jobs | III quarter of 2018
|  |  | 63.1.2 | Improvement of the quality of MLA requests by introducing a request to collect information about the assets of suspects abroad, and requests for seizure/confiscation abroad | RPPO |  | Improvement of the quality of MLA requests by applying the developed guidance | Increase in the number of MLA requests containing a request to collect information about the assets of suspects located abroad, or requests for seizure/confiscation abroad | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from the III quarter of 2018
|  |  | 63.1.3 | Delivery of additional training of Financial investigations Unit staff in relation to the identification of proceeds from crime located abroad | Police Academy, RPPO, Supreme Court of Cassation, MoI |  | 1 training cycle delivered | Training reports Training evaluation forms | No additional costs - to be covered by current staff within their current jobs | Continuously, starting from the III quarter of 2018
|  |  | 63.1.4 | Delivery of joint training of public prosecutors and judges relative to the possibility of improvement of international cooperation in the area of tracing and seizing/confiscating proceeds from crime located abroad |  |  | One cycle of each basic and advanced training for deputy public prosecutors and judges in special anti-corruption departments delivered | Training reports Training evaluation forms | Funds from the Council of Europe project | Continuously, starting from the III quarter of 2018
| 64.1 | Strengthening of capacities of public prosecutors offices and courts concerning seizure/confiscation of proceeds | 64.1.1 | Delivery of training on the application of provisional measures - Articles 147 and 540 of the CPC, seizure of proceeds - Articles 91 and 92 CC, seizure security measure - Article 87 CC, especially value-based confiscation | Police Academy | Supreme Court of Cassation, RPPO | One cycle of each basic and advanced training for deputy public prosecutors and judges in special anti-corruption departments delivered | Training reports Training evaluation forms | Funds from the Council of Europe project/Republic of Serbia budget - no costs | Continuously, starting from the III quarter of 2018
| 65.1 | Improve the capacities of the misdemeanour court | 65.1.1 | Hold training for judges of the Misdemeanour Appellate Court related to the application of the AML/CFT Law | Police Academy, High Judicial Council | Supreme Court of Cassation, Misdemeanour Appellate Court, foreign partners | 1 training cycle for each delivered | Training reports Training evaluation forms | Funds from the Council of Europe project/Republic of Serbia budget - no costs | Continuously, starting from the III quarter of 2018
| 66.1 | Improve the capacities of the commercial court | 66.1.1 | Hold training for judges of the Commercial Court related to the application of the AML/CFT Law | Police Academy, High Judicial Council | Supreme Court of Cassation, Commercial Court, foreign partners | 1 training cycle for each delivered | Training reports Training evaluation forms | Funds from the Council of Europe project/Republic of Serbia budget - no costs
| 67.1 | Improve the capacities of authorities to better recognise ML/TF risks when controlling cross-border transportation of cash | 67.1.1 | Delivery of training at various levels (basic, advanced, specialised) on ML/TF risks, trends and typologies | Customs Administration Border Police Directorate | APML, MoI, prosecutor’s office, commercial and misdemeanour courts | 1 training cycle of each basic, advanced and specialised training for the staff of Customs Administration and Border Police Directorate | Training reports Training evaluation forms | Funds from the Council of Europe project/Republic of Serbia budget - no costs | Continuously, starting from the III quarter of 2018
| 68.1 | Strengthening of capacities of the Tax Administration - Tax Police with respect to prevention of money laundering | 68.1.1 | Delivery of training related to recognising of ML typologies and methods | APML |  | 1 training cycle of each basic, advanced and specialised training for the TA staff | Training reports Training evaluation forms | Funds from the Council of Europe project/Republic of Serbia budget - no costs | Continuously, starting from the III quarter of 2018
| 69.1 | Strengthening of APML capacities | 69.1.1 | Delivery of 3 specialised trainings/workshops for APML staff on tax crimes | Tax Administration | APML | Number of trainings delivered | Training reports Training evaluation forms | No additional costs - to be covered by current staff within their current jobs | End of 2019
|  |  | 69.1.2 | Delivery of 3 specialised trainings/workshops for APML staff on criminal legislation | RPPO | APML
|  |  | 69.1.3 | Delivery of 4 specialised trainings/workshops for APML staff on intelligence analysis | BIA, VBA, MoI | APML
| 70.1 | Improve the knowledge of regulations and practices related to legal entities and legal arrangements (trusts) | 70.1.1 | Delivery of training by foreign FIUs and other relevant foreign authorities | APML | Under projects of foreign FIUs and international organisations (OSCE etc.) | Number of trainings delivered | Training reports Training evaluation forms | EUR 50,000 for 2019 / Council of Europe/OSCE/International partners project Republic of Serbia budget - no costs | End of 2019
| 71.1 | Improve knowledge of operation of legal entities registered in offshore areas | 71.1.1 | Delivery of 3 training events by FIUs with significant experience working with companies registered in offshore areas. | APML | Under projects of foreign FIUs and international organisations (OSCE etc.) | Number of trainings delivered | Training reports Training evaluation forms | EUR 50,000 for 2019 / Council of Europe/OSCE/International partners project Republic of Serbia budget - no costs | End of 2019
| 72.1 | Strengthen the capacities of supervisors for the application of AML/CFT legislation | 72.1.1 | Delivery of training related to AML/CFT supervision | Supervisory authorities | Foreign partners | Number of trainings delivered | Workshop reports, Training evaluation forms | Council of Europe project | Continuously, starting from September 2018
Insufficient awareness of new products | 73.1 | Improve knowledge on the use of new products for the purpose of ML/TF | 73.1.1 | Delivery of training for AML/CFT authorities related to new products | APML | Foreign partners | Number of trainings delivered | Workshop reports, Training evaluation forms | Costs of implementation of this activity will be covered by international partners | Continuously, starting from December 2018
Insufficient awareness of misuse of products in the financial market (capital market, market for negotiable instruments, foreign currency operations, etc.) | 74.1 | Improve the knowledge of products that may be misused | 74.1.1 | Delivery of training for AML/CFT authorities | Supervisory authorities | APML, RPPO. MoI, TA, CA | Number of trainings delivered | Workshop reports, Training evaluation forms | Costs of implementation of this activity will be covered by international partners | Continuously, starting from December 2018
Insufficient AML/CFT training of lawyers - Serbian Bar Chamber members | 75.1 | Improve the capacities of lawyers to understand their obligations under the AML/CFT Law | 75.1.1 | Delivery of additional training of analysts in the Serbian Bar Chamber | Serbian Bar Association (SBA) | APML | Number of trainings delivered | SBA Report | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  | 75.1.2 | Delivery of additional training of lawyers/members of the Serbian Bar Chamber | Serbian Bar Association (SBA) | APML | Number of trainings delivered | SBA Report | No additional costs - to be covered by current staff within their current jobs | September 2018
Inadequate STR and SAR reporting by exchange offices | 76.1 | Improve the capacities of obliged entities and supervisors in relation to STR/SAR reporting | 76.1.1 | Delivery of training for more efficient filling of forms for STRs/SARs and for better understanding of the reports | APML, Tax Administration | Serbian Chamber of Commerce | Number of trainings delivered | Lead institution’s work reports | No additional costs - to be covered by current staff within their current jobs | December 2018
TERRORIST FINANCING
Insufficient supervision of the NPO sector by the competent institutions with the aim of mitigating the vulnerability of the CFT system, insufficient number and inadequate training of inspectors in the competent authorities for checking the compliance with regulations by associations | 77.1 | Strengthening the capacities of the Working group established by the Government to perform supervisory inspection | 77.1.1 | Appointment of the WG members | Government Supervisory Inspection Coordination Commission | Ministry of Public Administration and Local Self-Government, Ministry of Culture and Information, SBRA, Office for Cooperation with Civil Society | WG members appointed | Report to the Coordination Commission | Budget - No additional costs | July 2018 | Priority activity
|  |  | 77.1.2 | Definition of a plan of activities |  |  | A plan of activities adopted | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | July 2018 | Priority activity
|  |  | 77.1.3 | Analysis of needs for staff required to supervise compliance by associations |  |  | Staff needs analysis made. | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | August and September 2018 | Priority activity
|  |  | 77.1.4 | Coordination of inspectors of various authorities in charge of controlling the compliance of associations |  |  | A plan of activities adopted | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | September 2018 | Priority activity
|  |  | 77.1.5 | Delivery of training to inspectors of competent institutions for checking consistency of the NPO activities with their objectives as stated in the statutes and checking whether the use of their assets is consistent with the statutory objectives, for the purpose of mitigating TF risks |  |  | Number of trainings delivered | Report to the Coordination Commission | Budget - an assessment will be available after the analysis | Continuously, in line with the overall objective achievement timeline | Priority activity
|  |  | 77.1.6 | Development of an annual plan of supervision over NPOs |  |  | Supervision plan developed | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | August and September 2018 | Priority activity
|  |  | 77.1.7 | Carrying out of inspections over the NPO sector |  |  | Number of inspections carried out over the NPO sector | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | Continuously, in line with the overall objective achievement timeline | Priority activity
|  |  | 77.1.8 | Reporting by the WG to the Coordination Commission for Supervisory Inspections |  |  | Report made | Report to the Coordination Commission | No additional costs - to be covered by current staff within their current jobs | Continuous, 3 months | Priority activity
Potential issues with the provisions of the Law on Freezing of Assets with the Aim of Preventing Terrorism concerning the - taking over of list of persons designated by the United Nations Security Council and other international organisations of which the Republic of Serbia is a member in the original in the English language and published on the website of the Administration for the Prevention of Money Laundering without publication in the RS Official Gazette - APML’s supervisory role under this Law | 78.1 | Analyse the Law on Freezing of Assets with the Aim of Preventing Terrorism and review comparative practices in relation to the problems that present a source of vulnerability | 78.1.1 | Establishment of an interagency working group to analyse the Law on Freezing of Assets with the Aim of Preventing Terrorism with respect to the problems that present a source of vulnerability, its efficiency and recommend appropriate solutions | Serbian Government |  | Government conclusion on the establishment of the working group | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | September 2018
|  |  | 78.1.2 | Development of an analysis of the Law on Freezing of Assets with the Aim of Preventing Terrorism with respect to the problems that present a source of vulnerability, its efficiency and recommend appropriate solutions | Working group | Ministry of Finance - APML, Ministry of Foreign Affairs, Ministry of Justice, MoI, MTTT, Directorate for Management of Seized/Confiscated Assets | Report on the analysis of the Law on Freezing of Assets with the Aim of Preventing Terrorism | WG work report to be submitted to the Government | No additional costs - to be covered by current staff within their current jobs | December 2018
Inadequate resources of the APML’s CTF Team | 79.1 | Strengthen the administrative and technical capacities and know-how of the newly recruited staff | 79.1.1. | Recruitment of new staff | APML | Serbian Government | Increased number of staff at the APML’s CTF Team | APML work report | Provided for in the budget under activity 19.1.1 | September 2018
|  |  | 79.1.1. | Training for the new staff on the use of the APML’s analytical tools |  |  | Training delivered | APML work report | No additional costs - to be covered by current staff within their current jobs | December 2018
|  |  |  | Implement the strengthening of technical capacities and know-how of the newly recruited staff |  |  | Equipment purchased | APML work report | Reallocation of current resources | December 2018
Insufficient customs officers’ knowledge of how to identify goods of strategic relevance | 80.1 | Improve the capacities of the Customs Administration to actually recognise dual-use goods, arms and military equipment | 80.1.1 | Delivery of training for customs officers | Ministry of Finance - Customs Administration, Sector for Tariffs, customs officers certified for this type of training | APML | Number of trainings delivered | Customs Administration report | No additional costs - to be covered by current staff within their current jobs | Continuously, in line with the overall objective achievement timeline
Lack of a list of persons, Serbian citizens, designated as terrorists and/or to be financing terrorism | 81.1 | Prepare lists of persons, Serbian citizens, designated as terrorists and/or to be financing terrorism | 81.1.1 | Identification of potential persons and collection of opinions from the competent authorities for designation | Prosecutor’s Office, BIA, MoI, APML | Serbian Government | Proposal prepared and submitted to the Government | Proposal to the Government for a list of Serbian citizens to be designated | No additional costs - to be covered by current staff within their current jobs | July 2018
|  |  | 81.1.2 | Submission of a proposal to designate |  |  | Proposal prepared and submitted to the Government | Proposal to the Government for a list of Serbian citizens to be designated | No additional costs - to be covered by current staff within their current jobs | July 2018
|  |  | 81.1.3 | Adoption of a domestic lists of designated persons |  |  | Proposal prepared and submitted to the Government | Official Gazette of the Republic of Serbia | No additional costs - to be covered by current staff within their current jobs | July 2018